## Gantt Chart
TurfSync – Turf Schedule & Booking Management System ¦ Incremental Development Model Gantt Chart
AIUB ¦ Dept. of Computer Science ¦ CSC 2210 – OOP 2 ¦ Fall 2025-2026 |  |  |  | Project: 5 Jan – 30 Apr 2026 (17 Weeks) |  |  |  | Team Kingsman – Group 5 ▸ Supervisor: Sadman Rafi
[8 empty] | January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  |  | April 2026
# | Increment | Task / Deliverable | Responsible | Start Wk | End Wk | Dur. (Wks) | Status | W1 5 Jan | W2 12 Jan | W3 19 Jan | W4 26 Jan | W5 2 Feb | W6 9 Feb | W7 16 Feb | W8 23 Feb | W9 2 Mar | W10 9 Mar | W11 16 Mar | W12 23 Mar | W13 30 Mar | W14 6 Apr | W15 13 Apr | W16 20 Apr | W17 27 Apr
| Pre-Dev | PRE-DEVELOPMENT ▸ Project Initiation |  |  |  |  | ACTIVE
1 | Pre-Dev | Team Formation & Role Assignment | All Members | 1 | 1 | 1 | Complete
2 | Pre-Dev | Problem Domain Research & Background Study | All Members | 1 | 1 | 1 | Complete
3 | Pre-Dev | Project Proposal & Scope Definition | All Members | 1 | 2 | 2 | Complete
4 | Pre-Dev | Target User Group Identification | All Members | 1 | 2 | 2 | Complete
5 | Pre-Dev | Technology Stack Selection (C# / WinForms / SQL Server) | All Members | 1 | 2 | 2 | Complete
6 | Pre-Dev | Development Model Selection ▸ Incremental Model Chosen | All Members | 2 | 2 | 1 | Complete
7 | Pre-Dev | Risk Assessment & Mitigation Planning | All Members | 2 | 2 | 1 | Complete
| Planning | REQUIREMENTS ANALYSIS & PLANNING |  |  |  |  | ACTIVE
8 | Planning | Functional Requirements Elicitation (41 Items) | All Members | 2 | 3 | 2 | Complete
9 | Planning | Non-Functional Requirements (Security / Performance / Usability) | All Members | 2 | 3 | 2 | Complete
10 | Planning | Business Rules Definition (R01–R15) | All Members | 2 | 3 | 2 | Complete
11 | Planning | Use Case Identification (Admin / Manager / Staff / Player) | All Members | 3 | 3 | 1 | Complete
12 | Planning | PRD Draft v1.0 & Feature Backlog | Fairuz / Iftakher | 3 | 3 | 1 | Complete
| Architecture | SYSTEM ARCHITECTURE & DATABASE DESIGN |  |  |  |  | ACTIVE
13 | Architecture | RBAC Architecture (Admin / Manager / Staff / Player) | All Members | 3 | 4 | 2 | Complete
14 | Architecture | OOP Class Hierarchy Design (Encapsulation, Inheritance, Polymorphism) | All Members | 3 | 4 | 2 | Complete
15 | Architecture | Entity Relationship Diagram (ER Diagram) | All Members | 3 | 4 | 2 | Complete
16 | Architecture | Database Normalization to 2NF (8 Tables) | All Members | 4 | 4 | 1 | Complete
17 | Architecture | UML Diagrams (Use Case, Activity, Class Diagrams) | All Members | 4 | 5 | 2 | Complete
18 | Architecture | UI / UX Wireframe Design (All Role Dashboards) | All Members | 4 | 5 | 2 | Complete
19 | Architecture | ADO.NET Data Access Layer Architecture | Iftakher / Ariful | 4 | 5 | 2 | Complete
| INC 1 | INCREMENT 1 — AUTHENTICATION & FOUNDATION (Core Working Build) |  |  |  |  | ACTIVE
| INC 1 | ► INC 1 Requirements Analysis & Detailed Design
20 | INC 1 | INC1: Scope — Authentication Module Specification | All Members | 4 | 5 | 2 | Complete
21 | INC 1 | INC1: DB Schema Design — Users Table + Constraints | Iftakher | 5 | 5 | 1 | Complete
| INC 1 | ► INC 1 Implementation (Coding)
22 | INC 1 | TurfSyncDB Setup — SQL Server Database Creation | Iftakher | 5 | 5 | 1 | Complete
23 | INC 1 | Users Table — Schema, FK Constraints, Password Hashing (SHA-256) | Iftakher | 5 | 5 | 1 | Complete
24 | INC 1 | DB Connection Layer — ADO.NET Connection Manager | Ariful | 5 | 6 | 2 | Complete
25 | INC 1 | Player Sign-Up Form — All Fields + Validation [TC_01] | Iftakher | 5 | 6 | 2 | Complete
26 | INC 1 | Player Login Form — Auth + Session Initialization [TC_02] | Iftakher | 6 | 6 | 1 | Complete
27 | INC 1 | Admin Login — Role Redirect to Admin Dashboard | Fairuz | 6 | 6 | 1 | Complete
28 | INC 1 | Manager Login — Role Redirect to Manager Dashboard | Tariqul | 6 | 6 | 1 | Complete
29 | INC 1 | Staff Login — Role Redirect to Staff Dashboard | Tahosin | 6 | 7 | 2 | Complete
30 | INC 1 | Logout (All Roles) — Session Clear + Confirmation Dialog | All Members | 7 | 7 | 1 | Complete
31 | INC 1 | Role-Based Access Control — Screen-Level Guard | All Members | 7 | 7 | 1 | Complete
| INC 1 | ► INC 1 Testing
32 | INC 1 | Unit Testing — Authentication Module [TC_01, TC_02] | Iftakher | 7 | 7 | 1 | Complete
33 | INC 1 | Code Review & Integration Verification | All Members | 7 | 7 | 1 | Complete
M1 | INC 1 | ★ MILESTONE 1 — Working Authentication System Delivered |  | 7 | 7 |  | ✔ Done | [6 empty] | ◆
| INC 2 | INCREMENT 2 — ADMIN MODULE (Built on Increment 1) |  |  |  |  | ACTIVE
| INC 2 | ► INC 2 Requirements Analysis & Design
34 | INC 2 | INC2: Admin Module Specification & UI Wireframes | Fairuz | 7 | 8 | 2 | Complete
35 | INC 2 | INC2: DB Schema — turfLocation, Packages, turfBookings Tables | Iftakher | 7 | 8 | 2 | Complete
| INC 2 | ► INC 2 Implementation (Coding)
36 | INC 2 | Admin Dashboard — Summary Cards + Navigation Panel | Fairuz | 8 | 8 | 1 | Complete
37 | INC 2 | Staff & Manager Account Management — Add/Edit/Deactivate/Delete [TC_03] | Fairuz | 8 | 9 | 2 | Complete
38 | INC 2 | Turf Location Management — CRUD + Operating Hours Validation | Fairuz | 8 | 9 | 2 | Complete
39 | INC 2 | Turf Package Management — Name/Duration/Price + IsAvailable [TC_04] | Fairuz | 9 | 9 | 1 | Complete
40 | INC 2 | Manual Turf Booking (Admin) — Walk-in Customer Booking | Ariful | 9 | 10 | 2 | Complete
41 | INC 2 | Auto Timestamp Logging — CreatedAt DEFAULT GETDATE() on all tables | Iftakher | 9 | 10 | 2 | Complete
42 | INC 2 | DataGridView Integration — Sorting, Filtering, Row Selection | Fairuz / Ariful | 10 | 10 | 1 | Complete
| INC 2 | ► INC 2 Testing
43 | INC 2 | Unit Testing — Admin Module (CRUD Operations) [TC_03, TC_04] | Fairuz | 10 | 10 | 1 | Complete
44 | INC 2 | Integration Test — Auth → Admin (Login to Dashboard flow) | All Members | 10 | 10 | 1 | Complete
M2 | INC 2 | ★ MILESTONE 2 — Working Admin System Delivered |  | 10 | 10 |  | ✔ Done | [9 empty] | ◆
| INC 3 | INCREMENT 3 — MANAGER & STAFF MODULES (Built on Increment 2) |  |  |  |  | ACTIVE
| INC 3 | ► INC 3 Requirements Analysis & Design
45 | INC 3 | INC3: Manager & Staff Module Specification | Tariqul / Tahosin | 9 | 10 | 2 | Complete
46 | INC 3 | INC3: DB Schema — TurfSchedule + StaffManagement Tables | Iftakher | 9 | 10 | 2 | Complete
| INC 3 | ► INC 3 Implementation — Manager Module
47 | INC 3 | Manager Dashboard — Cards, Schedule Overview, Real-time Data | Tariqul | 10 | 10 | 1 | Complete
48 | INC 3 | Schedule Management — View/Update/Filter by Date/Location/Status | Tariqul | 10 | 11 | 2 | Complete
49 | INC 3 | Pricing Control — Auto Night/Weekend Surcharges (R14) | Tariqul | 11 | 11 | 1 | Complete
50 | INC 3 | Manual Price Update — Selected Schedule Price Override | Tariqul | 11 | 11 | 1 | Complete
51 | INC 3 | Booking Approval — Approve/Reject Pending Requests + Concurrent Lock [TC_07] | Tariqul | 11 | 12 | 2 | Complete
52 | INC 3 | Maintenance Management — Mark Slots / Revert to Available (R09) | Tariqul | 12 | 12 | 1 | Complete
| INC 3 | ► INC 3 Implementation — Staff Module
53 | INC 3 | Staff Dashboard — Assigned Schedules Overview | Tahosin | 11 | 11 | 1 | Complete
54 | INC 3 | Ground Preparation Checklist — Turf Brushed / Trash / Water Bottles [TC_09] | Tahosin | 12 | 12 | 1 | Complete
55 | INC 3 | Equipment & Facility Status — Lights / Football / Bibs / Cones | Tahosin | 12 | 12 | 1 | Complete
56 | INC 3 | Arrival Tracking — Mark Player Arrived / Not Arrived (R12) | Tahosin | 12 | 13 | 2 | Complete
57 | INC 3 | Schedule Duration Monitor — Upcoming / In Progress / Completed | Tahosin | 13 | 13 | 1 | Complete
| INC 3 | ► INC 3 Testing
58 | INC 3 | Unit Testing — Manager Module (Approval, Pricing flows) [TC_07] | Tariqul | 13 | 13 | 1 | Complete
59 | INC 3 | Unit Testing — Staff Module (Prep, Equipment, Arrival) [TC_09] | Tahosin | 13 | 13 | 1 | Complete
60 | INC 3 | Integration Test — Admin → Manager → Staff (end-to-end ops) | All Members | 13 | 13 | 1 | Complete
M3 | INC 3 | ★ MILESTONE 3 — Working Operations System Delivered |  | 13 | 13 |  | ✔ Done | [12 empty] | ◆
| INC 4 | INCREMENT 4 — PLAYER BOOKING & RATING (Built on Increment 3) |  |  |  |  | ACTIVE
| INC 4 | ► INC 4 Requirements Analysis & Design
61 | INC 4 | INC4: Booking & Rating Module Specification | Ariful / Tahosin | 12 | 13 | 2 | Complete
62 | INC 4 | INC4: DB Schema — PendingRequests, BookingHistory, ServiceRatings | Iftakher | 12 | 13 | 2 | Complete
| INC 4 | ► INC 4 Implementation — Player Profile
63 | INC 4 | Player Dashboard — Navigation Panel + Quick-Access Feature Cards | Ariful | 13 | 13 | 1 | Complete
64 | INC 4 | View Profile — Read-only Personal Info Display | Ariful | 13 | 14 | 2 | Complete
65 | INC 4 | Edit Profile — Validated Field Updates + Username Uniqueness (R07) | Ariful | 14 | 14 | 1 | Complete
66 | INC 4 | Change Password — Current Password Verification + Hashing (R08) [TC_10] | Iftakher | 14 | 14 | 1 | Complete
| INC 4 | ► INC 4 Implementation — Booking Module
67 | INC 4 | Book Turf Slot — Search/Filter + Concurrency Lock (R01 No Double Booking) [TC_05] | Ariful | 14 | 15 | 2 | Complete
68 | INC 4 | Cancel Booking — 2-hr Cutoff (R02) + 80% Refund Calculation (R03) [TC_06] | Ariful | 14 | 15 | 2 | Complete
69 | INC 4 | Reschedule Booking — New Slot Assignment + Transaction Rollback (R15) | Ariful | 15 | 15 | 1 | Complete
70 | INC 4 | Track Booking Status — Real-Time Countdown Timer + Color-Coded States | Ariful | 15 | 15 | 1 | Complete
| INC 4 | ► INC 4 Implementation — Match History & Rating
71 | INC 4 | View Match History — Arrived Records Only (R12) | Tahosin | 15 | 15 | 1 | Complete
72 | INC 4 | Rate Turf Service — 6-Dimension Rating + Arrival Eligibility (R04, R05) [TC_08] | Tahosin | 15 | 16 | 2 | Complete
73 | INC 4 | Update Rating — Pre-filled Form + DB Update | Tahosin | 16 | 16 | 1 | Complete
74 | INC 4 | Delete Rating — Confirmation + Re-Eligibility Restore | Tahosin | 16 | 16 | 1 | Complete
| INC 4 | ► INC 4 Testing
75 | INC 4 | Unit Testing — Player Module (Profile, Booking, Rating) [TC_05,06,08,10] | Ariful / Tahosin | 16 | 16 | 1 | Complete
76 | INC 4 | Business Rules Validation (R01–R15 all rules verified) | All Members | 16 | 16 | 1 | Complete
M4 | INC 4 | ★ MILESTONE 4 — Complete Player System Delivered |  | 16 | 16 |  | ✔ Done | [15 empty] | ◆
| Final | FINAL PHASE — INTEGRATION, SYSTEM TESTING & DELIVERY |  |  |  |  | ACTIVE
| Final | ► System Integration & Full Test Suite
77 | Final | End-to-End Integration Testing (All 4 Increments unified) | All Members | 16 | 17 | 2 | Complete
78 | Final | Full Test Suite Execution (TC_01 – TC_10) ▸ 6 Pass / 4 Fail Logged [All TCs] | All Members | 16 | 17 | 2 | Complete
79 | Final | Bug Fixing & Regression Testing (Failed cases resolved) | All Members | 17 | 17 | 1 | Complete
80 | Final | Performance Testing (500 Records < 2 sec, Booking < 1 sec) | Iftakher / Ariful | 17 | 17 | 1 | Complete
81 | Final | Security Testing (SQL Injection, Password Hashing, Session Expiry) | Tariqul | 17 | 17 | 1 | Complete
82 | Final | DB Integrity Verification (FK Constraints, 2NF, No Anomalies) | Iftakher | 17 | 17 | 1 | Complete
| Final | ► Documentation & Submission
83 | Final | PRD v2.0 Finalization (All 41 Items verified) | Fairuz / Iftakher | 16 | 17 | 2 | Complete
84 | Final | Technical Documentation (Architecture, DB Schema, UML) | Tariqul / Ariful | 16 | 17 | 2 | Complete
85 | Final | Project Report Compilation (Introduction, Features, ER, UML) | All Members | 17 | 17 | 1 | Complete
86 | Final | Test Case Document (TC_01–TC_10 with Pass/Fail Results) | All Members | 17 | 17 | 1 | Complete
87 | Final | Presentation Preparation (Slides + Demo Script) | All Members | 17 | 17 | 1 | Complete
M5 | Final | ★ MILESTONE 5 — FINAL PROJECT SUBMISSION & PRESENTATION |  | 17 | 17 |  | ✔ Done | [16 empty] | ◆
LEGEND: | Pre-Development | Planning | Architecture | Increment 1 | Increment 2 | Increment 3 | Increment 4 | Final Phase | ★ Milestone
Note: This Gantt chart follows the Incremental Software Development Model. Each increment delivers a fully functional working build, layered on the previous. Test Cases [TC_01–TC_10] mapped against implementation tasks. Business Rules [R01–R15] enforced per increment.

## Project Overview
TurfSync – Project Overview ¦ Incremental Development Model
PROJECT INFORMATION
Course |  | CSC 2210 – Object Oriented Programming 2
Department |  | Dept. of Computer Science – Faculty of Science & Technology
University |  | American International University–Bangladesh (AIUB)
Semester |  | Fall 2025–2026
Supervisor |  | Sadman Rafi
Team |  | Team Kingsman – Group 5
Dev Model |  | Incremental Software Development Model
Tech Stack |  | C# (.NET), Windows Forms, SQL Server, ADO.NET
Timeline |  | 5 January 2026 – 30 April 2026 (17 Weeks)
Total Tasks |  | 87 Tasks ¦ 5 Milestones ¦ 10 Test Cases ¦ 15 Business Rules
TEAM MEMBERS & RESPONSIBILITIES
# | Name | Student ID |  | Primary Responsibility |  |  | Test Cases
1 | Fairuz Faiyaz | 23-54707-3 |  | Admin Module, Docs, PRD |  |  | TC_03, TC_04
2 | Md. Iftakher Hossain | 23-54694-3 |  | Authentication, DB Setup, ADO.NET |  |  | TC_01, TC_02
3 | Tariqul Islam | 23-54685-3 |  | Manager Module, UML Diagrams |  |  | TC_07
4 | Tahosin Iftiak Tonoy | 23-54682-3 |  | Staff Module, Rating Module |  |  | TC_08, TC_09
5 | Md. Ariful Hoque | 23-54680-3 |  | Player Booking, Cancel, Reschedule |  |  | TC_05, TC_06
INCREMENTAL BUILD SUMMARY
Increment | Phase | Weeks | Key Deliverables | Modules | Test Cases | DB Tables | Business Rules | Milestone
Pre-Dev | Initiation | 1–2 | Project Proposal, Scope, Risk Assessment | Planning | – | – | – | –
Planning | Requirements | 2–3 | Functional (41), Non-Functional, Business Rules, PRD v1.0 | All Modules | – | – | R01–R15 defined | –
Architecture | Design | 3–5 | ER Diagram, 2NF Normalization, UML, Wireframes, OOP Design | All | – | 8 Tables designed | – | –
Increment 1 | Authentication | 4–7 | Working Login/Signup for all 4 roles, Session Mgmt, RBAC | Auth | TC_01, TC_02 | Users | R06,R07,R08,R10 | MS1: Auth System
Increment 2 | Admin | 7–10 | Admin Dashboard, User/Location/Package Mgmt, Manual Booking | Admin | TC_03, TC_04 | turfLocation, Packages, turfBookings | R07 | MS2: Admin System
Increment 3 | Manager+Staff | 9–13 | Scheduling, Pricing, Approval, Maintenance, Prep, Arrival | Manager+Staff | TC_07, TC_09 | TurfSchedule, StaffManagement | R09,R12,R14 | MS3: Ops System
Increment 4 | Player | 12–16 | Booking, Cancel, Reschedule, Track, History, Rating | Player | TC_05,06,08,10 | PendingRequests, BookingHistory, ServiceRatings | R01–R05,R11,R13,R15 | MS4: Player System
Final Phase | Integration | 16–17 | End-to-End Testing, All 10 TCs, Bug Fix, Docs, Submission | All | TC_01–TC_10 | – | All verified | MS5: Submission
WHY INCREMENTAL DEVELOPMENT MODEL?
✔ Early Working Software: Each increment delivers a runnable, testable build — not just documentation.
✔ Risk Reduction: Core authentication & DB risks addressed first in INC1 before building advanced features.
✔ Modular Development: Admin, Manager, Staff, and Player modules developed independently yet integrated seamlessly.
✔ Parallel Testing: Each increment has its own unit testing phase, allowing TC_01–TC_10 to be mapped per module.
✔ Flexibility: Requirements for Phase 2 (Booking, Rating) refined after Phase 1 stability was confirmed.
✔ Suits Academic Timeline: Clear milestone deliverables match course submission checkpoints.
✔ Client Feedback Ready: Working builds at Milestones 1–4 can be demonstrated to supervisor at any stage.

## Test Case Tracker
TurfSync – Test Case Tracker ¦ TC_01 – TC_10 ¦ Group 5
TC ID | Module | Test Title | Tester | Date | Priority | Increment | Status | Pass/Fail | Notes
TC_01 | Auth – Player Sign-Up | Verify successful player registration with valid inputs | Md Iftakher Hossain | 23/04/2026 | High | INC 1 | Complete | ✔ PASS | All 4 steps passed
TC_02 | Auth – Player Login | Verify player login with valid and invalid credentials | Md Iftakher Hossain | 23/04/2026 | High | INC 1 | Complete | ✔ PASS | All 4 steps passed
TC_03 | Admin – User Mgmt | Verify admin can add, edit, deactivate a staff account | Fairuz Faiyaz | 23/04/2026 | High | INC 2 | Complete | ✔ PASS | CRUD operations verified
TC_04 | Admin – Packages | Verify admin can create and manage turf packages | Fairuz Faiyaz | 23/04/2026 | High | INC 2 | Complete | ✔ PASS | Package lifecycle tested
TC_05 | Booking – Book Slot | Verify player can search and book an available turf slot | Md. Ariful Hoque | 23/04/2026 | High | INC 4 | Complete | ✗ FAIL | Concurrent lock edge case
TC_06 | Booking – Cancel | Verify player can cancel booking with 80% refund | Md. Ariful Hoque | 23/04/2026 | High | INC 4 | Complete | ✗ FAIL | 2-hr cutoff timer issue
TC_07 | Manager – Approval | Verify manager can approve/reject booking requests | Tahosin Tonoy | 23/04/2026 | High | INC 3 | Complete | ✔ PASS | Approval flow confirmed
TC_08 | Player – Rating | Verify player can rate turf after arrival confirmation | Tahosin Tonoy | 23/04/2026 | Medium | INC 4 | Complete | ✗ FAIL | Rating eligibility filter bug
TC_09 | Staff – Ground Prep | Verify staff can update ground preparation checklist | Tariqul Islam | 23/04/2026 | Medium | INC 3 | Complete | ✔ PASS | All 3 checkboxes functional
TC_10 | Auth – Change Pwd | Verify player can change password with current verification | Tariqul Islam | 23/04/2026 | High | INC 4 | Complete | ✗ FAIL | Hashing mismatch on save
SUMMARY: Total = 10 ¦ Pass = 6 ¦ Fail = 4 ¦ Pass Rate = 60%